Tournament Director Sample Timeline

| Pre-Tournament 1 year; -Secure course. 4-6 Months. 6-9 months; -Committee formed -Post info on CGA -Save the date cards -Design flyers and brochures. 4-6 months; -Print brochures -Contact sponsors -Format and rules. 3 month; -Mail brochures. 2 months; -Increased publicity -E-mail invites -Course meetings. 1 month; -Order prizes -Secure staffing. 3 weeks; -Finalize rules -Finalize contests -Staff assignments -Place orders -Final e-mail invite. 2 weeks; -Player confirmations -Staff meeting -Entry deadline. 1 week; -Pairings finalized -Confirm numbers -Receive orders. 3 days; -Pairings to course. Confirmation to all players & Sponsors. 2 days; -Pack supplies. |  |  |  | Post-Tournament 1 day; -Financial Analysis. 1 week; -Thanks you notes -Follow up e-mail -Evaluations -Pay bills. |
| --- | --- | --- | --- | --- |